## recommendations
2018-07-01
Call It Spring
www.callitspring.com SEO recommendations
Scope | Recommendation | Comments | Priority level
Crawl
Robots.txt file | See robots.txt | Standby. | Important
Hreflang | See /hreflang/hreflang-tags.html or /hreflang/sitemap-hreflang.xml | Implement hreflang tags on each page or add an hreflang sitemap, whatever is easiest. | Critical
Infinite scroll | See pagination.html | In progress. | Important
Search Console setup | Verify media subdomain on Search Console. Add http & https versions of the domains | None. | Important
Linking | See links.html | In progress. | Normal
Indexing
Product Urls (colours) | Have one, non-colour specific, URL per product. Load the colours in the same page, using JS to lazy Load the other product images. | In progress. | Critical
Product availability | Leave the product page as is for temporarily unavailable products. Redirect discontinued product pages to the most relevant category/PDP. | What will be the server status code on temporarily unavailable products? What will be the server status code on discontinued products (redirections)? | Critical
Image Optimization | Add alt attribute on product images. | In progress. | Normal
Open graph | See open-graph.html | In progress. | Normal
Store locator |  | Standby. | Important
Sitemap index | See sitemap-index.html | In progress. | Important
Sitemap pages | See sitemap-pages.html | In progress. | Important
Sitemap images | See sitemap-images.html | In progress. | Important
SERP
Structured data markup | See structured-data.html | In progress. | Normal
UX-related
Breadcrumbs - Product Pages | On product pages: add a link to the homepage in position 1. | None. | Normal
PageSpeed | See performance.html Deliver site assets (product images, hero/content images and navigation icons) through a content delivery network and set a server caching rule. Media cache should be busted when assets are modified. | In Progress. | Important

## design scope
Components & Pages | SEO Benefit
Global banner | y
PDP 5 angles TBC | y
P00-Homepage | y
P01-Gender_Landing | y
P02-PLP | y
P03-PLP_Deluxe | y
P04-PLP_Sales | y
P05-Me_to_We | y
P06-Trend | y
P07-Instashop | y
P08-Wishlist | y
P09-PDP | y
P10-Gift_Card | y
P15-International | y | s
X01-Footer | y
X06-Search | y
X07-Navigation | y
X08-Filter | y
X09-Store_Locator | y
P11-Checkout | n
P12-Account | n
P13-404 | n
P14-Legal | n
X00 - Styleguide | n
X02-Cookie | n
X03-Modal_Account_Sign_In | n
X04-Modal_Error | n
X05-Size_Guide | n
X10-Promos | n
T01-VOC | n
T02-True_Fit | n
T03-Live_Chat | n

## data
Critical
Important
Normal
Low